## Timeline
Week | Title | Difficulty level | Description | Due Date | Status | Comments
1 | Complete Requirements Document | Medium | Finalize the document and get sign off from instructor | 2025-05-09 | In progress | Get feedback from instructor
2 | Environment Setup & Development Planning | Medium | - Install WordPress, WooCommerce, and Elementor on a local or staging server. - Configure essential plugins (e.g., Product Add-Ons). - Refine initial Figma wireframes for homepage, product, cart, and checkout pages. - Define site structure (menus, categories, page list). | 2025-05-16
3 | UI Layout Design with Elementor | Medium | - Build homepage, shop, product, cart, and checkout layouts using Elementor. - Use placeholder images and text based on wireframes. - Ensure pages are navigable and visually structured. | 2025-05-23
| WooCommerce Customization (Backend) | Hard | - Configure WooCommerce settings: categories, tax, shipping/pickup, and custom fields for cake options. - Install and customize WooCommerce Product Add-Ons plugin. - Begin custom PHP or filter/hook logic for cake customization if required. | 2025-05-23
4 | UI-Backend Integration | Hard | - Connect product customization fields to WooCommerce cart logic. - Verify product customization reflects in cart, order, and email summary. - Ensure full product ordering flow works (add to cart, update cart, proceed to checkout). | 2025-05-30
5 | Responsive Design and Styling | Medium | - Test and refine layout across desktop, tablet, and mobile. - Add visual polish: fonts, color themes, spacing, and minor animations. - Use custom CSS to fix Elementor limitations where needed. | 2025-06-06
| Testing & Debugging | Medium | - Test all Shopper user stories (browsing, customizing, ordering). - Test Manager features in WooCommerce dashboard (order status, product edits). - Fix any broken logic or UI bugs. - Test edge cases (missing fields, invalid orders, etc.). | 2025-06-06
| Final Review & Delivery | Easy | - Conduct user walkthrough or usability test (if available). - Finalize images and text content. - Make final UI adjustments. - Prepare site for demo or deployment. | 2025-06-06
6
7
| Presentation | Easy | Complete project presentation requirements. |  | Not started
Note on B1: SWD: What is the component you are working on?
Note on C1: SWD: What is your perception of how difficult this component will be? Easy ¦ Medium ¦ Difficult
Note on D1: SWD: A brief description of the tasks for this component.
Note on E1: SWD: Your target date for completion
Note on F1: SWD: Not Started In Progress Stalled Completed
Note on G1: SWD: Notes or reminders concerning this component.